## LaraBids Project Log Update
Date | Description | Query | Status
2026-02-02 | Bid migrations/models, BidServices, Request layers, updated Auction & UserDashboard controllers for bidding. | No | completed
2026-02-03 | Fixed time settings, added My-Auctions & Past-Auctions, Ajax Watchlist functionality, and Search UX improvements. | No | completed
2026-02-04 | UI/UX improvements, Profile section, Header profile image fetch, and Public Profile page/controller implementation. | No | completed
2026-02-05 | Session limits (max 3), Session middleware, Sub-category logic, Parent/Child relationships, and Pagination UI fix. | No | completed
2026-02-06 | Min/Max bid increment logic, bid validations, and Quick Bid buttons (100, 300, 500 etc.). | No | completed